## Start Here
APPOINTMENT HELPER ¦ PROJECT CONTROL
A practical execution system for a solo developer: DDD + layered server actions + TDD + UI/UX design system. Auth/RBAC/RCAC are intentionally excluded from assigned tasks.
Purpose | Turn the existing codebase into a beta-ready product. Track workflow completion, not just files or code volume.
Core rule | Work vertically by user workflow, but build each workflow in a deliberate order: define outcome → map UI/data contract → domain tests (Red) → implement domain/service/repository/action → UI → integration/E2E → polish.
Architecture assumption | Server Action / safeAction → service (business orchestration/rules) → repository/database. Queries may read through query modules/repositories. Keep React components focused on presentation and interaction.
TDD loop | RED: write a failing test for a business rule. GREEN: implement the smallest correct change. REFACTOR: simplify without changing behavior. Then integration test at the DB boundary and E2E for critical user journeys.
Do not test everything equally | Prioritize availability/time calculations, booking conflicts and concurrency, appointment lifecycle, cancellation/rescheduling, business-hour validation, and core CRUD workflows.
Task limit | Keep exactly one task In Progress. If blocked, record the blocker and move it to Blocked before starting another task.
Done means | Acceptance criteria pass; validation/errors/loading/empty/success states are covered where applicable; responsive UI and accessibility basics are checked; relevant tests pass; no known blocker remains.
Anti-procrastination rule | At the start of a session, choose one task that can be completed in 1–4 hours. At the end, record evidence and the very next action. No polishing beyond acceptance criteria.
Suggested sequence | 1) inventory actual state; 2) close critical workflow gaps; 3) complete customer booking journey; 4) complete business appointment-management journey; 5) finish UI design system/responsive pass; 6) regression and beta release gate.
Status definitions | Backlog = not ready; Ready = clear and startable; In Progress = active; Blocked = dependency/decision; Done = acceptance criteria met; Deferred = deliberately outside beta.
Estimate rule | Estimates are guesses, not commitments. Use actual hours to improve future estimates. Break tasks larger than 4 hours into smaller independently verifiable tasks.
Important | Feature/task rows below are a starter backlog based on known project context. Validate each status against the current repo; do not treat suggested statuses as verified facts.
LIVE SNAPSHOT
Total tasks
Done
In progress
Blocked
Critical tasks not done

## Nov 2 Demo Plan
APPOINTMENT HELPER — DEMO DEADLINE PLAN
Target: credible potential-customer demo by Monday, Nov 2, 2026 ¦ Budget: 9 hours maximum ¦ Auth/RBAC/RCAC implementation remains with developer
Operating rule: audit before building. Demonstrate one reliable golden path, not the whole product. If the audit finds major missing functionality, reduce the demo scope instead of exceeding the time budget.
Day / Date | Time Budget | Outcome | Exact Work | Workbook Tasks | Evidence / Exit Criteria | Do NOT Do | Fallback if Behind
Wed Oct 28 | 1.25 h | Know what is actually demoable | Run app/build; list the routes needed for one business setup → customer booking → business appointment view. Trace each critical path through UI → server action → service → repository. Mark workbook inventory as working / broken / unverified. Choose one demo store and seed data. | T001; T029 | A written 3-step demo path; top 1–3 blockers identified; inventory updated with evidence. Stop auditing once scope is clear. | No redesign, no broad code cleanup, no auditing every feature equally. | If the full journey is unclear, select the strongest existing path and define a narrow demo scenario.
Thu Oct 29 | 1.5 h | Close the highest-impact integration gap | Work on the single blocker that prevents the golden path from running end to end. Preserve server action → service/rules → repository. Add a focused test for the failure or contract being fixed. | Pick only the relevant task among T007, T011, T013, T017, T020 | One blocker resolved and verified through the real path; focused test passes. Commit/save a known-good checkpoint. | Do not work on multiple features in parallel. Do not build a new subsystem. | If integration is too large, demo the working persisted workflow that already exists and clearly defer the incomplete step.
Fri Oct 30 | 1.5 h | Protect the demo's highest-risk business rule | Test and verify the exact booking/availability behavior the demo will show: valid slot, invalid slot, and existing/conflicting booking if supported by current implementation. Fix only a defect that could produce an incorrect booking or misleading confirmation. | T006, T009, T010, T015, T016, T017 — choose only what the audit says is relevant | A small risk-based test set passes; booking result is persisted and confirmation is truthful. No known critical correctness defect in the chosen scenario. | No exhaustive edge-case matrix; no broad test-count target; no concurrency rewrite unless the current demo is unsafe. | Use a controlled, pre-verified demo slot and seeded data; do not claim unsupported guarantees.
Sat Oct 31 | 1.5 h | Make the golden path understandable | Polish only screens used in the demo. Ensure visible labels, sensible navigation/back behavior, form validation, loading/pending, empty/error/success states, and no obvious mobile overflow. Use existing components; fix only issues visible in the chosen flow. | T004, T005, T008, T012, T014, T021 — only relevant items | A first-time viewer can follow the golden path without developer narration for every action; no blocking UI state. | No full design-system overhaul, animations, advanced filters, QR, or secondary pages. | Use desktop/tablet demo viewport if responsive polish cannot be completed everywhere; record the limitation.
Sun Nov 1 | 1.75 h | Verify, stabilize, and rehearse | Run targeted unit/integration tests, production build, and one end-to-end/manual smoke journey. Reset seed data and rehearse the demo twice. Capture known limitations and prepare a short demo script. | T018; T027; selected Beta Gate items | Build passes; golden path succeeds twice from a clean starting state; known limitations are written down; no unresolved demo-blocking bug. | No new features. No refactor unless needed to fix a demonstrated defect. | If the full booking journey remains broken, switch to a truthful guided demo of the strongest completed workflow and label unfinished steps.
Mon Nov 2 | 0.5 h | Preflight and demonstrate | Check environment/configuration, login/account access, seed data, network, and final golden path. Avoid deploying new code unless a critical fix is necessary and can be re-verified. | T028; user-owned auth/RBAC/RCAC release review | Demo environment opens; demo account works; one clean run succeeds; backup plan/data are ready. | No elective changes or last-minute visual polish. | If production deployment is not safe, demonstrate from a stable staging/local environment and state that clearly.
TOTAL PLANNED | 8.0 h | Keep 1–2 hours of real-life buffer if possible; the plan itself uses 8 hours.
DEFINITION OF DONE FOR THIS DEADLINE
1. A specific target customer and demo scenario are chosen.
2. The selected golden path works from a clean starting state and uses real persisted data where the workflow claims it does.
3. Availability/booking rules used in the demo are verified; no knowingly misleading slot or confirmation.
4. The critical UI states are clear enough for a customer-facing demonstration.
5. Relevant tests and production build pass; deployment/auth/configuration are checked to the extent required by the demo environment.
6. Unfinished capabilities are documented as limitations, not represented as completed.
ANTI-PROCRASTINATION RULE
At the start of a work block, write the exact deliverable. Work on one task only. If blocked for 15 minutes, write the blocker and choose the smallest testable alternative. End every block by recording evidence and the next action. The goal is shipped proof, not hours spent thinking about the project.

## Feature Inventory
FEATURE INVENTORY
Assess each user-facing workflow across domain/backend, UI, integration, and tests. Starter statuses are deliberately 'Verify' unless already confirmed by the user.
ID | Workflow / Area | Domain / Backend | UI / UX | Integration | Tests | Beta Priority | Feature Status | Depends On | Notes / Acceptance Outcome
F01 | Store onboarding & settings | Verify | Verify | Verify | Verify | High | Not Assessed |  | Business can configure the minimum store profile needed to operate.
F02 | Service management | Verify | Verify | Verify | Verify | High | Not Assessed | F01 | Create/edit/list services with validation and clear feedback.
F03 | Staff management | Verify | Verify | Verify | Verify | High | Not Assessed | F01 | Create/edit/list staff and connect staff to store/services as intended.
F04 | Business hours & closures | Verify | Verify | Verify | Verify | Critical | Not Assessed | F01 | Valid hours, closed days, and exceptions are represented correctly.
F05 | Staff availability & time off | Verify | Verify | Verify | Verify | Critical | Not Assessed | F03; F04 | Staff schedules/time off are editable and reflected in availability.
F06 | Availability calculation | Verify | Verify | Verify | Verify | Critical | Not Assessed | F02; F04; F05 | Correct slots based on service duration, buffers, schedules, closures, and existing bookings.
F07 | Customer booking wizard | Verify | Verify | Verify | Verify | Critical | Not Assessed | F02; F03; F06 | Customer can select service/staff/date-time and submit a valid booking.
F08 | Booking conflict / concurrency protection | Verify | N/A | Verify | Verify | Critical | Not Assessed | F06; F07 | Two overlapping bookings cannot both succeed; server-side enforcement is authoritative.
F09 | Appointment lifecycle & management | Verify | Verify | Verify | Verify | Critical | Not Assessed | F07 | Valid state transitions, status updates, cancellation/no-show/reschedule rules.
F10 | Check-in flow / QR | Verify | Verify | Verify | Verify | High | Verify | F09 | Check-in works for the intended appointment states and user journey.
F11 | Appointment history | Verify | Verify | Verify | Verify | Medium | Not Assessed | F09 | History filters and empty/loading/error states are understandable.
F12 | Store discovery / public pages | Verify | Verify | Verify | Verify | Medium | Not Assessed | F01; F02 | Public discovery pages show correct available business/service information.
F13 | Profile & account settings (non-auth scope) | Verify | Verify | Verify | Verify | Medium | Not Assessed |  | Profile data display/edit behavior; auth and permission implementation excluded.
F14 | Notifications / booking feedback | Verify | Verify | Verify | Verify | High | Not Assessed | F07; F09 | Clear booking confirmation and operational feedback; external delivery only if beta scope requires it.
F15 | API routes used by booking/review/staff/store | Verify | N/A | Verify | Verify | High | Not Assessed | Relevant workflow | Validate input/output contracts, failures, and integration with consumers.
F16 | Responsive app shell & navigation | N/A | Verify | Verify | Verify | High | Not Assessed |  | Navigation, page shell, and core layouts work at mobile/tablet/desktop widths.
F17 | Shared UI design system | N/A | Verify | Verify | Verify | High | Not Assessed |  | Tokens, typography, spacing, buttons, forms, feedback, cards, dialogs, tables, accessibility.
F18 | Production readiness / beta deployment | Verify | Verify | Verify | Verify | Critical | Not Assessed | Critical workflows | Production config, migrations, logs/errors, backup/rollback awareness, smoke test.

## Task Backlog
TASK BACKLOG
Keep tasks small and verifiable. Confirm or change each task against the current codebase. Auth, RBAC, and RCAC implementation are excluded by request.
Task ID | Feature ID | Layer / Workstream | Task | Acceptance Criteria / Evidence | TDD / Test Level | Priority | Estimate (hrs) | Status | Dependency | Actual (hrs) | Next Action / Blocker
T001 | F00 | Planning | Audit existing routes, domains, components, and tests | Feature Inventory updated with actual status; identify missing/incomplete workflows. | Inventory | Critical | 2 | Ready |  |  | List routes and map them to user workflows.
T002 | F17 | UI/UX design system | Audit current shadcn/Tailwind components and visual inconsistencies | Create short list of shared tokens/components to standardize; avoid unnecessary redesign. | Manual + component | High | 2 | Backlog | T001 |  | Record existing patterns before changing them.
T003 | F17 | UI/UX design system | Define core UI tokens and usage rules | Document typography, spacing, colors, radii, borders, focus, error/success/warning states. | Component / visual | High | 3 | Backlog | T002 |  | Keep the system minimal and aligned to existing shadcn setup.
T004 | F17 | UI/UX design system | Standardize shared form and feedback components | Inputs, labels, validation, pending/disabled, empty/loading/error/success states are consistent. | Component | High | 4 | Backlog | T003 |  | Prioritize components used by critical workflows.
T005 | F16 | Frontend | Audit responsive shell/navigation across core routes | Critical routes have consistent navigation and no horizontal overflow at mobile/tablet/desktop widths. | Component / manual | High | 3 | Backlog | T001 |  | Create a route/viewport checklist.
T006 | F04 | Domain / TDD | Test business-hours and time-block validation rules | Write failing tests for valid/invalid ranges, boundary values, day selection, and malformed input; then make green. | Unit: domain/schema | Critical | 2 | Backlog | T001 |  | RED → GREEN → REFACTOR; reuse current schema tests where appropriate.
T007 | F04 | Backend layers | Verify business-hours save/read flow | Query returns persisted values; server action validates input and delegates to service; service applies rules; repository persists. | Integration: action/service/repository | Critical | 3 | Backlog | T006 |  | Use existing layer conventions; avoid duplicate DB calls.
T008 | F04 | Frontend | Finish business-hours UI states | Display current values/defaults, save feedback, validation errors, empty/loading states, and responsive layout. | Component + integration | High | 3 | Backlog | T007; T004 |  | Confirm default values and edit behavior.
T009 | F05 | Domain / TDD | Test staff availability rules | Tests cover weekday mapping, time ranges, time off/closures, and invalid/overlapping blocks as required by domain rules. | Unit: domain | Critical | 3 | Backlog | T001 |  | Test pure rules before database wiring.
T010 | F06 | Domain / TDD | Test slot generation and availability calculation | Cover service duration/buffer, business hours, staff hours, existing appointments, closures, timezone, boundaries, and no-slot cases. | Unit: domain | Critical | 4 | Backlog | T006; T009 |  | This is high risk; define expected behavior before implementation.
T011 | F05 | Backend layers | Verify staff availability read/write flow | Server action → service → repository; persisted schedules load correctly and updates return a typed success/error response. | Integration: service/repository/action | Critical | 3 | Backlog | T009 |  | Auth/RBAC/RCAC are handled separately by the developer.
T012 | F05 | Frontend | Finish staff availability screen | Existing availability displays correctly; create/edit/delete flows work; loading/empty/error/success states and mobile layout pass. | Component + integration | Critical | 4 | Backlog | T011; T004 |  | Keep one task active; split further if over 4 hours.
T013 | F06 | Backend layers | Connect availability query to booking date selection | Query returns slots for selected staff/service/date using domain rules; no stale/mock data in production path. | Integration | Critical | 3 | Backlog | T010; T011 |  | Clarify when date changes trigger fetch/recalculation.
T014 | F07 | Frontend | Finish booking wizard UI states | Service/staff/date-time/review steps have clear progress, back navigation, validation, empty/loading/error states, and mobile layout. | Component | Critical | 4 | Backlog | T004; T013 |  | Use real contracts; temporary mock data only if clearly isolated.
T015 | F07 | Domain / TDD | Test booking command rules | Tests cover required fields, duration, eligibility, time validity, status defaults, and invalid requests. | Unit: domain/service | Critical | 3 | Backlog | T010 |  | Do not duplicate implementation details in tests.
T016 | F08 | Domain / TDD | Test overlapping booking and concurrency protection | Overlaps are rejected at the authoritative server/database boundary, including concurrent requests where applicable. | Unit + integration | Critical | 4 | Backlog | T015 |  | Do not rely on UI availability alone to prevent double booking.
T017 | F07 | Backend layers | Verify create-booking action → service → repository | Action validates input; service enforces rules; repository persists; failures are typed and no partial invalid booking remains. | Integration | Critical | 4 | Backlog | T015; T016 |  | Confirm transaction/constraint strategy in current architecture.
T018 | F07 | Integration / E2E | Verify complete customer booking journey | A user can select service/staff/date/time, review, submit, and see persisted confirmation; invalid/conflicting attempt fails clearly. | E2E smoke | Critical | 4 | Backlog | T014; T017 |  | Use Playwright if configured; otherwise record current E2E tooling decision.
T019 | F09 | Domain / TDD | Test appointment state transitions | Valid transitions succeed; invalid transitions fail; cancellation/no-show/reschedule behavior follows explicit rules. | Unit: domain/service | Critical | 3 | Backlog | T001 |  | Write the allowed transition table before coding.
T020 | F09 | Backend layers | Verify appointment management mutations | Status changes and reschedule/cancel actions pass through server action → service → repository and preserve invariants. | Integration | Critical | 4 | Backlog | T019 |  | Keep transition rules in domain/service, not UI components.
T021 | F09 | Frontend | Finish appointment list/detail/actions UI | Useful status display, filters where required, action confirmation, pending/error/success states, responsive layout. | Component + integration | High | 4 | Backlog | T020; T004 |  | Avoid adding filters not needed for beta.
T022 | F10 | Workflow | Verify check-in / QR flow | QR or manual check-in resolves the correct appointment and respects valid appointment state; failures are clear. | Unit + integration + E2E smoke | High | 3 | Backlog | T019 |  | Decide whether QR is required for first beta.
T023 | F11 | Frontend + query | Complete appointment history workflow | Correct data, useful empty/loading/error states, basic filtering if required, and responsive display. | Component + integration | Medium | 3 | Backlog | T020 |  | Defer advanced filtering if not beta-critical.
T024 | F12 | Frontend + query | Complete public store/service discovery | Public pages load correct data and guide users into booking; loading/empty/error states are handled. | Component + integration | Medium | 3 | Backlog | F01; F02; F07 |  | Confirm scope based on intended beta users.
T025 | F14 | Domain / backend | Verify booking confirmation behavior | Booking result is communicated clearly; notification delivery is only included if required for beta; failures don't misreport booking status. | Unit + integration | High | 3 | Backlog | T017 |  | Separate in-app confirmation from external email/SMS delivery.
T026 | F15 | API contracts | Audit workflow API routes | Request validation, response shape, failure cases, and consumers are verified; remove stale or unused paths only with evidence. | Integration | High | 3 | Backlog | T001 |  | List current API routes and map each to a consumer.
T027 | F00 | Regression | Run focused regression after critical workflows | Relevant Vitest suites and production build pass; no known regressions in critical flows. | Regression | Critical | 2 | Backlog | T018; T020 |  | Capture command and result/date as evidence.
T028 | F18 | Release | Create beta smoke-test checklist and deployment verification | Production environment, migrations, core booking flow, appointment management, and error logging are checked. | E2E + manual | Critical | 3 | Backlog | T027 |  | Only mark release-ready after a real deployed smoke test.
T029 | F00 | Planning | Choose next task at end of each session | Record completed evidence and one concrete next action; avoid opening another task without closing/blocking current one. | Process | High | 0.25 | Ready | T001 |  | Five-minute closeout; no punishment for honest blockers.

## Weekly Commitments
WEEKLY COMMITMENTS
Commit to outcomes, not hours spent. Plan conservatively; review honestly. One In Progress task at a time.
Week Starting | Commitment / Outcome | Task IDs | Planned Hours | Actual Hours | Status | Evidence / What shipped | If unfinished: why? | Next commitment
2026-10-28 | Audit and choose the demo golden path | T001; T029 | 1.25 |  | Ready | Route/workflow map + top blockers |  | Fix one blocker only
2026-10-29 | Resolve the single highest-impact integration gap | Relevant one of T007/T011/T013/T017/T020 | 1.5 |  | Backlog | Real path works + focused test |  | Verify booking correctness
2026-10-30 | Verify booking/availability rule used in demo | Relevant subset of T006/T009/T010/T015/T016/T017 | 1.5 |  | Backlog | Risk-based tests pass; persisted result |  | Polish only golden-path UI
2026-10-31 | Polish only the customer-facing golden path | Relevant subset of T004/T005/T008/T012/T014/T021 | 1.5 |  | Backlog | Clear form feedback; no blocking UI state |  | Regression and rehearse
2026-11-01 | Regression, build, and rehearse twice | T018; T027; selected Beta Gate items | 1.75 |  | Backlog | Build + smoke journey pass twice |  | Monday preflight
2026-11-02 | Final preflight and customer demo | T028; user-owned auth/RBAC/RCAC review | 0.5 |  | Backlog | Demo environment and account verified |  | Use stable fallback environment

## Beta Gate
BETA RELEASE GATE
A beta is ready when critical user journeys work reliably—not when every feature is perfect. Mark each item only after evidence exists.
ID | Gate / Requirement | Required for Beta? | Status | Evidence / Test / Link | Owner | Notes / Risk
B01 | Business can configure store basics | Yes | Not Assessed |  | Developer
B02 | Business can create/edit services and staff | Yes | Not Assessed |  | Developer
B03 | Business hours and staff availability are correct | Yes | Not Assessed |  | Developer
B04 | Availability respects schedules, service duration/buffer, closures, and existing bookings | Yes | Not Assessed |  | Developer
B05 | Booking is validated server-side and conflicting bookings cannot both succeed | Yes | Not Assessed |  | Developer
B06 | Customer completes booking and receives truthful confirmation | Yes | Not Assessed |  | Developer
B07 | Business can view and manage appointment lifecycle | Yes | Not Assessed |  | Developer
B08 | Critical screens handle loading, empty, error, success, and pending states | Yes | Not Assessed |  | Developer
B09 | Critical workflows are responsive and keyboard/accessibility basics checked | Yes | Not Assessed |  | Developer
B10 | Relevant unit and integration tests pass | Yes | Not Assessed |  | Developer
B11 | Critical booking journey E2E/smoke test passes | Yes | Not Assessed |  | Developer
B12 | Production build passes and deployed app uses correct configuration | Yes | Not Assessed |  | Developer
B13 | Production database migration and rollback/recovery approach understood | Yes | Not Assessed |  | Developer
B14 | Auth/RBAC/RCAC review completed by developer | Yes | Not Assessed |  | Developer | Assigned to user per request; track here only as a release gate, not as backlog work.
B15 | Check-in/QR workflow | Decide | Not Assessed |  | Developer | Include only if required for target beta users.
B16 | History, discovery, advanced filters, external notifications | Decide | Not Assessed |  | Developer | Confirm what is essential versus post-beta.

## Decisions
DECISIONS & BLOCKERS
Record choices that would otherwise keep you cycling between alternatives. Keep decisions brief and reversible when possible.
ID | Date | Decision / Question | Options Considered | Decision | Reason / Trade-off | Revisit When